## DASHBOARD
LONGREIN — WEEKLY DASHBOARD
Pirmadienio 8:00 ritualas — užpildyk WEEK_INPUT eilutę, čia pamatysi savaitės status'ą
Dabartinė savaitė #: | 1 | ← keisk šitą skaičių
Mėnuo: |  |  | Savaitės pradžia: | Master Calendar:
P0 šią savaitę:
NORTH STAR — MRR
PIPELINE
FM trial #: |  |  | Demos sched: | Demos done:
Paid signups: |  |  | Lost/churn:
PRODUCT
DAU/WAU %: |  |  | Horses on: | NPS:
Open bugs: |  |  | Uptime %:
FINANSAI
Cash €: |  |  | MRR €: | Burn €:
Runway (mo): |  |  | AR overdue €:
MARKETING
IG followers: |  |  | IG reach 7d: | Landing visits:
Sign-up rate %: |  |  | Posts shipped: | Email list:
ASMENINĖ DARNA — burnout pulse
Hours Longrein: |  |  | Hours TJK: | Sleep h/night:
Riding sessions: |  |  | Sunday off?
Energy 1-10: |  |  | Cynicism 1-10: | Efficacy 1-10:
STATUS šią savaitę: |  |  | Ship done? | (R/Y/G arba TAIP/NE rankiniu)
Notes:

## WEEK_INPUT
CONTEXT |  |  |  |  | PIPELINE |  |  |  |  | PRODUCT |  |  |  |  | FINANSAI |  |  |  |  | MARKETING | [5 empty] | ASMENINĖ | [7 empty] | RETRO
Wk # | Mėnuo | Pradžios data | Master Calendar fazė | P0 šios savaitės | FM trial # | Demos sched | Demos done | Paid signups | Lost/churn | DAU/WAU % | Horses on platform | NPS | Open bugs | Uptime % | Cash € | MRR € | Burn € | Runway mo | AR overdue € | IG followers | IG reach 7d | Landing visits | Sign-up rate % | Posts shipped | Email list | Hours Longrein | Hours TJK | Sleep h/night | Riding sessions | Sunday off | Energy 1-10 | Cynicism 1-10 | Efficacy 1-10 | Status R/Y/G | Ship done? | Notes
1 | M1 | 2026-05-23 | M1 — FM onboarding sprint (week 1)
2 | M1 | 2026-05-30 | M1 — FM onboarding sprint (week 2)
3 | M1 | 2026-06-06 | M1 — FM onboarding sprint (week 3)
4 | M1 | 2026-06-13 | M1 — FM onboarding sprint (week 4)
5 | M2 | 2026-06-20 | M2 — Retention proof
6 | M2 | 2026-06-27
7 | M2 | 2026-07-04
8 | M2 | 2026-07-11
9 | M3 | 2026-07-18 | M3 GATE — Retention gate (8/10 active?)
10 | M3 | 2026-07-25
11 | M3 | 2026-08-01
12 | M3 | 2026-08-08
13 | M4 | 2026-08-15 | M4 — Conversion push begins
14 | M4 | 2026-08-22
15 | M4 | 2026-08-29
16 | M4 | 2026-09-05
17 | M5 | 2026-09-12
18 | M5 | 2026-09-19 | M5 — Conversion + content scale
19 | M5 | 2026-09-26
20 | M5 | 2026-10-03
21 | M6 | 2026-10-10
22 | M6 | 2026-10-17 | M6 GATE — Conversion proof (2+ paid?)
23 | M6 | 2026-10-24
24 | M6 | 2026-10-31
25 | M7 | 2026-11-07
26 | M7 | 2026-11-14
27 | M7 | 2026-11-21 | M7 — Paid customer scale
28 | M7 | 2026-11-28
29 | M8 | 2026-12-05
30 | M8 | 2026-12-12
31 | M8 | 2026-12-19 | M8 — Pre-recalibration analysis
32 | M8 | 2026-12-26
33 | M9 | 2027-01-02
34 | M9 | 2027-01-09
35 | M9 | 2027-01-16 | M9 GATE — Pricing recalibration
36 | M9 | 2027-01-23
37 | M10 | 2027-01-30
38 | M10 | 2027-02-06
39 | M10 | 2027-02-13
40 | M10 | 2027-02-20 | M10 — Scale operations
41 | M11 | 2027-02-27
42 | M11 | 2027-03-06
43 | M11 | 2027-03-13
44 | M11 | 2027-03-20 | M11 — Year-2 prep
45 | M12 | 2027-03-27
46 | M12 | 2027-04-03
47 | M12 | 2027-04-10
48 | M12 | 2027-04-17 | M12 GATE — Year-1 verdict
49 | M13 | 2027-04-24
50 | M13 | 2027-05-01
51 | M13 | 2027-05-08
52 | M13 | 2027-05-15

## TRENDS
TRENDS — auto-generated charts (atsinaujina kai pildai WEEK_INPUT)

## GATES
GATES — kvartaliniai sprendimai
Pildoma 1× per ketvirtį: M3 / M6 / M9 / M12 / M15 / M18. Sprendimas CONTINUE / PIVOT / KILL — be šių sprendimų strategija drift'ina.
M3 GATE — Retention
Date target: | 2026-08-23
KPI: | 8/10 FMs aktyvūs (weekly login)
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | ICP recalibration — yra ne tas tipas? funkcijos blogos? onboarding'as silpnas?
Notes / why:
M6 GATE — Conversion
Date target: | 2026-11-23
KPI: | 2+ paid customers, MRR €180+
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | Pricing arba messaging klaida — A/B test'uoti pricing page, perskaityti FM exit interviews
Notes / why:
M9 GATE — Pricing
Date target: | 2027-02-23
KPI: | 10 paid customers reached, MRR €900+
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | Recalibrate €3/horse — gali tekti pakelti į €3.50 jei retention OK, arba mažinti į €2.50 jei sales blok'inasi
Notes / why:
M12 GATE — Year-1 verdict
Date target: | 2027-05-23
KPI: | 35 paid customers, MRR €3,045, ARR €36,540
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | CONTINUE Year 2 (DACH) / PIVOT (B2C? Different vertical?) / KILL (return to TJK only)
Notes / why:
M15 GATE — DACH prep
Date target: | 2027-08-23
KPI: | DE waitlist 200+, EN docs done, DE-native hire pipeline
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | Delay DACH 6 mo, focus LT/PL
Notes / why:
M18 GATE — DACH launch
Date target: | 2027-11-23
KPI: | First 3 DE customers, EN/DE landing live
Actual (fill):
Decision (CONTINUE/PIVOT/KILL):
If FAIL: | Pull back to LT/PL only, reassess Year 3
Notes / why:

## ALERTS_LOG
Data | Wk # | Alert tipas | Metrika | Veiksmas | Rezultatas
Pavyzdžiai 'Alert tipas': BURNOUT / FINANSAI / RETENTION / PIPELINE / PRODUCT

## README
LONGREIN — WEEKLY DASHBOARD YEAR 1
Pildoma kiekvieną pirmadienį 8:00–8:30. Sekmadienio retro 21:50–22:00.
KAIP NAUDOTI
1) Eik į WEEK_INPUT — pildai 1 eilutę per savaitę, 52 eilutės iš viso.
2) DASHBOARD sheet automatiškai parodo dabartinę savaitę su alert'ais (žalia/geltona/raudona).
3) TRENDS sheet — auto-charts (MRR, customers, hours, IG followers).
4) GATES sheet — pildoma 1× per ketvirtį (M3 / M6 / M9 / M12 — sprendimai CONTINUE / PIVOT / KILL).
5) ALERTS_LOG — laisva forma rašai kas suveikė tą savaitę ir ką darei.
FAILĄ ATIDARYK PIRMADIENĮ. DURYS UŽDARYTOS. KAVA. 30 MIN. KIEKVIENĄ SAVAITĘ.
DAŽNIAUSIOS KLAIDOS
• Skip'inti pildymą blogą savaitę (ypač tada reikia).
• Pildyti 3 P0 vietoj 1 (1 P0 = vienas. Ne trys.).
• Ignoruoti raudonas asmeninės darnos eilutes (burnout = projekto pabaiga).
• Pridėti naujų metrikų be pašalinimo senų (limit = vienas dashboard puslapis).
GATES SCHEDULE
M3 = 2026-08-23 — Retention gate (8/10 FMs aktyvūs?)
M6 = 2026-11-23 — Conversion proof (2+ paid customers?)
M9 = 2027-02-23 — Pricing recalibration (€3/horse veikia?)
M12 = 2027-05-23 — Year-1 verdict (€36K ARR? Continue Year 2?)
KEY TARGETS YEAR 1 (iš Master Calendar)
M1: 9/10 FMs aktyvūs ¦ IG followers 2,000
M2: 8/10 weekly login ¦ IG 5,000
M3: 8/10 retention ¦ IG 10,000
M6: 2+ paid customers ¦ MRR €180+
M9: 10 paid customers ¦ MRR €900+
M12: 35 paid customers ¦ MRR €3,045 ¦ ARR €36,540
REFERENCE DOCS (visi /APP/Longrein-Ops/)
• Longrein-Founder-Operational-Dashboard-2026-05-05.md (šio failo metodologija)
• Longrein-Master-Year1-Calendar-2026-05-02.md (datos, gates)
• Longrein-Year1-Financial-Model.xlsx (revenue/burn projekcijos)
• Longrein-Personal-Sustainability-Plan-2026-05-02.md (burnout boundaries)
• Longrein-FM-Customer-Success-Playbook-2026-05-02.md (retention metrics)